## Tasks
Tasks | Status | Goal | Priority | Target close date | Days until target date |  | Primary owner | Secundary owner | Progress % | Bottleneck | To-do action points | Next action due: | Finished action points | Result | Status / update | Actual close date | Additional/background info. | Date added
Set up of educational program for EMCM | 4. Ongoing |  | EMCM | 2016-01-01 | -218 | -218 | Sabine |  | 60 |  | implementation is still to proceed. Waiting for Juli | [6 empty] | 2015-09-15
Optimization of the TrainingsMatrix | 4. Ongoing |  | EMCM | 2016-01-01 | -218 | -218 | Sabine |  | 50 |  | 1 juli alle wijzigingen doorvooeren en beginenn met trainen. difference of opinio between Martijn en Tim is currently blocking progress |  | alles uitgewerkt en gepresenteerd aan middenkader |  |  |  |  | 2015-08-13
EBlinC systeem van Multisafe toegankelijk maken voor het gehele personeel | 2. To start |  | EMCM/LBM Europe | 2016-01-01 | -218 | -218 | sabine |  | 0 | [8 empty] | 2015-08-20
Researching Mocha | 4. Ongoing |  | Very Low |  | -42588 | -42588 | Sam |  | 0 | [8 empty] | 2016-08-06 12:04
Sign Up Page | 1. On hold | Front End Cleanup | Low |  | -42588 | -42588 | Sam |  | 0 | [8 empty] | 2016-08-06 12:13
Log In Page | 1. On hold | Front End Cleanup | Low |  | -42588 | -42588 | Sam |  | 0 | [8 empty] | 2016-08-06 13:11
Games Page | 1. On hold | Front End Cleanup | Low |  | -42588 | -42588 | Sam |  | 0 | [8 empty] | 2016-08-06 13:11
Go To Game View | 2. To start | Game Page | Critical | 2016-08-13 | 7 | 7 | Sam | Ryan | 0 | [8 empty] | 2016-08-06 12:50
Socket/View Joining Game | 2. To start | Transition Page | High | 2016-08-13 | 7 | 7 | Ryan |  | 0 | [8 empty] | 2016-08-06 12:53
Socket/View Creating Game | 2. To start | Transition Page | Critical | 2016-08-13 | 7 | 7 | Ryan | Sam | 0 | [8 empty] | 2016-08-06 12:54
Transitional Page | 2. To start | Transition Page | High | 2016-08-13 | 7 | 7 | Sam |  | 0 |  | Set up Angular controller with variable to control gameView vs transitionView | [6 empty] | 2016-08-06 12:55
In calender year 2016 entire EMCM staff are reviewed via a performance review | 4. Ongoing |  | EMCM | 2017-01-01 | 148 | 148 | sabine |  | 0 | [8 empty] | 2015-08-03
Route to gameView | 1. On hold | Game Page | Low |  | -42588 | -42588 | Ryan |  | 0 | [8 empty] | 2016-08-06 13:17
Pop Game Method in Game Hook | 1. On hold | Points | Low |  | -42588 | -42588 | Ryan |  | 0 | [8 empty] | 2016-08-06 13:22
Dealing | 1. On hold | Game Page | Medium |  |  | -42588 |  |  | 0
Excel Data Copying | 1. On hold |  | Low |  |  | -42588
-42588
-42588
-42588
-42588
-42588
-42588
-42588
-42588
1. On hold
2. To start
3. Priority
4. Ongoing
5. Behind planning
6. Completed
Formulas:
Date added = IF([Tasks]<>"", IF([Date added]="", NOW(), [Date added]), "")

## Goals
Front End | Back End | Status
Transition Page | Transition Page
Game Page | Game Page
Drag and Drop | Points
Request and Response Handlers | Runes
Socket Event Handlers | Scuttle
Victory | One Offs
Front End Cleanup | Victory

## Closed actions
Project | Date Closed | Date Due | Days Before Deadline | Percentage | Owner | Completed Steps | Result
RMA to EMCM
aap Item Entry
aap QC Entry
Archving Documents

## Legend
DropDowns
Very Low
Low
Medium
High
Critical